## Summary
Praxis Makes Perfect — Coding Time Analysis
~89 hours
Estimated total coding time based on git commit analysis
Project Timeline | 2026-01-16 to 2026-03-29
Calendar Span | 72 days
Active Work Days | 16 days
Total Commits | 73
Work Sessions | 26
Avg Hours / Active Day | 5.6
Development Phases
Phase | Hours | Commits | % Total
Early Mar: Restructure | 14.3 | 6 | 16%
Jan: Initial Build | 17.3 | 12 | 19%
Mar 18-21: Migration + Learning | 17.1 | 18 | 19%
Mar 22-25: Features Sprint | 22.9 | 18 | 26%
Mar 26-29: Polish & AI Tutor | 17.3 | 19 | 19%
Methodology & Caveats
Sessions: 3-hour gap between commits = new session.
Rates: ~100 lines/hr feature code (AI-assisted), ~1000 lines/hr data/JSON.
Batch commits estimated by total code volume, not timestamp span.
Daily cap: 14 hours maximum per day.
Known data commits (question banks) given reduced estimates.
CAVEAT: Actual time likely ±30%. Unmeasured: debugging, testing, research, design thinking.

## Daily Breakdown
Date | Day | Est. Hours | Commits | Lines Added | Cumulative
2026-01-16 | Fri | 0.1 | 1 | 1 | 0.1
2026-01-20 | Tue | 0.1 | 1 | 11000 | 0.2
2026-01-26 | Mon | 13 | 7 | 86654 | 13.2
2026-01-30 | Fri | 2.5 | 1 | 2079 | 15.7
2026-01-31 | Sat | 1.6 | 2 | 1540 | 17.3
2026-03-14 | Sat | 7.5 | 3 | 29818 | 24.8
2026-03-15 | Sun | 6.6 | 2 | 86682 | 31.4
2026-03-16 | Mon | 0.2 | 1 | 1 | 31.6
2026-03-18 | Wed | 9.4 | 13 | 9098 | 41
2026-03-20 | Fri | 7.7 | 5 | 11526 | 48.7
2026-03-22 | Sun | 5.5 | 6 | 23802 | 54.2
2026-03-23 | Mon | 12.8 | 8 | 69822 | 67
2026-03-24 | Tue | 4.6 | 4 | 498 | 71.6
2026-03-26 | Thu | 2.1 | 3 | 1501 | 73.7
2026-03-27 | Fri | 14 | 14 | 15875 | 87.7
2026-03-29 | Sun | 1.2 | 2 | 745 | 88.9

## Session Detail
Date | Start | End | Span (h) | Est. Hours | Commits | Insertions | Batch? | Primary Work
2026-01-16 | 00:10 | 00:10 | 0 | 0.1 | 1 | 1 |  | Initial commit
2026-01-20 | 19:09 | 19:09 | 0 | 0.1 | 1 | 11000 |  | Initial commit
2026-01-26 | 06:43 | 06:43 | 0 | 6 | 1 | 56895 |  | feat: Complete Adaptive Coaching System implementation
2026-01-26 | 10:46 | 10:51 | 0.08 | 4.4 | 2 | 28374 |  | Add deployment configs (+1 more)
2026-01-26 | 17:29 | 17:35 | 0.1 | 2.6 | 4 | 1385 |  | Integrate Firebase auth and Firestore progress storage (+3 more)
2026-01-30 | 00:00 | 00:00 | 0 | 2.5 | 1 | 2079 |  | Your update message
2026-01-31 | 22:57 | 22:57 | 0 | 1.6 | 2 | 1540 |  | Add Firebase authentication: email/password, Google OAuth, password reset (+1 more)
2026-03-14 | 03:40 | 03:41 | 0.02 | 7.5 | 3 | 29818 | Yes | Consolidate project documentation (+2 more)
2026-03-15 | 15:42 | 16:27 | 0.75 | 6.6 | 2 | 86682 |  | Update from AI assistant (+1 more)
2026-03-16 | 04:16 | 04:16 | 0 | 0.2 | 1 | 1 |  | Remove invalid submodule entry .claude/worktrees/bold-buck
2026-03-18 | 13:37 | 19:36 | 5.98 | 9.4 | 13 | 9098 |  | Fix Node health-check import crash and document bundle-size warnings (+12 more)
2026-03-20 | 01:12 | 01:29 | 0.29 | 1 | 2 | 69 |  | Add local-only repo hygiene rules (+1 more)
2026-03-20 | 09:47 | 09:59 | 0.21 | 4.2 | 2 | 9753 |  | Add Learning Path visual node map + module page (+1 more)
2026-03-20 | 17:30 | 17:30 | 0 | 2.5 | 1 | 1704 |  | Refine learner UI layout and document health-check status
2026-03-22 | 01:08 | 01:08 | 0 | 1 | 1 | 290 |  | fix: address post-audit feedback across stats, UX, and code quality
2026-03-22 | 20:18 | 22:32 | 2.24 | 4.5 | 5 | 23512 |  | feat: adaptive diagnostic, onboarding fixes, login copy, and study guide gating (+4 more)
2026-03-23 | 01:34 | 06:04 | 4.51 | 5.3 | 6 | 43908 |  | feat: module feedback cards, hint system, and struggling-skill alerts (+5 more)
2026-03-23 | 14:43 | 14:43 | 0 | 3.5 | 1 | 5478 |  | Add vocabulary glossary with dynamic module tooltips
2026-03-23 | 18:40 | 18:40 | 0 | 4 | 1 | 20436 |  | feat: Redemption Rounds, Study Notebook, module interactives polish
2026-03-24 | 08:26 | 12:16 | 3.83 | 4.6 | 4 | 498 |  | fix: consolidate assessment terminology to "adaptive diagnostic" throughout (+3 more)
2026-03-26 | 17:32 | 18:54 | 1.36 | 2.1 | 3 | 1501 |  | refactor: replace hardcoded proficiency thresholds with canonical constants (+2 more)
2026-03-27 | 00:52 | 00:55 | 0.05 | 4.2 | 3 | 2633 | Yes | feat: make users-online pill time-of-day aware (+2 more)
2026-03-27 | 07:52 | 08:06 | 0.23 | 1.8 | 2 | 1022 |  | feat: improve AI Tutor — fix quiz routing, artifact generation, and chip UX (+1 more)
2026-03-27 | 11:16 | 11:27 | 0.18 | 0.9 | 2 | 52 |  | fix: normalize artifact types from Claude + guard fill-in-blank download (+1 more)
2026-03-27 | 23:55 | 23:58 | 0.04 | 10.5 | 7 | 12168 | Yes | feat: Redemption Rounds v2 — quarantine system with blacklist exclusion (+6 more)
2026-03-29 | 10:42 | 10:44 | 0.03 | 1.2 | 2 | 745 |  | refactor: learning science alignment — P1–P6 (+1 more)

## Commit Log
# | Timestamp | Message | Files | Insertions | Deletions
1 | 2026-01-16 00:10:56 | Initial commit | 1 | 1 | 0
2 | 2026-01-20 19:09:10 | Initial commit | 45 | 11000 | 0
3 | 2026-01-26 06:43:48 | feat: Complete Adaptive Coaching System implementation | 111 | 56895 | 1909
4 | 2026-01-26 10:46:43 | Add deployment configs | 34 | 28372 | 3884
5 | 2026-01-26 10:51:21 | Fix build: exclude scripts from TypeScript check and use Vite build only | 2 | 2 | 1
6 | 2026-01-26 17:29:26 | Integrate Firebase auth and Firestore progress storage | 18 | 915 | 71
7 | 2026-01-26 17:31:40 | Phase 1: crash-proof results + safe profile defaults | 4 | 253 | 24
8 | 2026-01-26 17:33:24 | Phase 2.1: Upgrade Quick Diagnostic to 40Q with duplicate-proof selection | 2 | 41 | 10
9 | 2026-01-26 17:35:39 | Phase 2.2: Full Test 120Q with domain-balanced selection using largest remainder method | 3 | 176 | 8
10 | 2026-01-30 00:00:34 | Your update message | 22 | 2079 | 901
11 | 2026-01-31 22:57:50 | Add Firebase authentication: email/password, Google OAuth, password reset | 14 | 1377 | 113
12 | 2026-01-31 22:57:59 | Add deployment guide | 1 | 163 | 0
13 | 2026-03-14 03:40:16 | Consolidate project documentation | 47 | 2125 | 171
14 | 2026-03-14 03:40:48 | Normalize tooling and generated artifacts | 22 | 227 | 5157
15 | 2026-03-14 03:41:38 | Update application flows and study plan infrastructure | 84 | 27466 | 45054
16 | 2026-03-15 15:42:28 | Update from AI assistant | 79 | 85883 | 23060
17 | 2026-03-15 16:27:33 | Migrate from Firebase to Supabase | 16 | 799 | 632
18 | 2026-03-16 04:16:46 | Remove invalid submodule entry .claude/worktrees/bold-buck | 2 | 1 | 1
19 | 2026-03-18 13:37:43 | Fix Node health-check import crash and document bundle-size warnings | 2 | 39 | 4
20 | 2026-03-18 13:39:56 | Complete Firebase-to-Supabase migration and pre-launch cleanup | 49 | 1689 | 1251
21 | 2026-03-18 16:08:17 | Add StudyModesSection: gated Domain Review + Skill Review on home screen | 4 | 412 | 10
22 | 2026-03-18 16:17:42 | Show both domain and skill context on every practice question | 1 | 45 | 34
23 | 2026-03-18 16:37:13 | Add cumulative accuracy %, streak messages, and inactivity auto-logout to PracticeSession | 1 | 158 | 21
24 | 2026-03-18 16:41:48 | Fix dynamic all-time % and clarify overconfidence label | 1 | 19 | 5
25 | 2026-03-18 17:28:38 | Fluent practice: question retirement, context-aware navigation, relabelled cards | 2 | 419 | 263
26 | 2026-03-18 17:42:15 | Fix study plan generation truncation by raising max_tokens to 8000 | 1 | 1 | 1
27 | 2026-03-18 17:47:55 | Fix study plan Netlify function: Lambda format, routing, and token bump | 3 | 125 | 32
28 | 2026-03-18 18:00:21 | Add migration 0001: study_plans table + session ID columns | 1 | 34 | 0
29 | 2026-03-18 18:10:10 | Switch study plan generation to Netlify Background Function | 3 | 345 | 88
30 | 2026-03-18 18:13:19 | Update documentation: study guide bugs, Netlify rules, Supabase notes | 3 | 124 | 20
31 | 2026-03-18 19:36:33 | Rebuild study plan system: v2 architecture + auth fix | 22 | 5688 | 1339
32 | 2026-03-20 01:12:04 | Add local-only repo hygiene rules | 6 | 64 | 0
33 | 2026-03-20 01:29:19 | Upgrade Vite to patched v6 line | 2 | 5 | 1
34 | 2026-03-20 09:47:06 | Add Learning Path visual node map + module page | 12 | 4558 | 719
35 | 2026-03-20 09:59:25 | feat: onboarding, daily progress, proficiency layer, profile migration | 45 | 5195 | 1607
36 | 2026-03-20 17:30:49 | Refine learner UI layout and document health-check status | 24 | 1704 | 1379
37 | 2026-03-22 01:08:12 | fix: address post-audit feedback across stats, UX, and code quality | 7 | 290 | 130
38 | 2026-03-22 20:18:02 | feat: adaptive diagnostic, onboarding fixes, login copy, and study guide gating | 51 | 4068 | 697
39 | 2026-03-22 20:26:46 | fix: login page mobile scroll — use h-screen + flex layout for proper scrolling | 1 | 2 | 2
40 | 2026-03-22 20:38:20 | chore: update .gitignore for working artifacts and generated files | 1 | 13 | 0
41 | 2026-03-22 20:49:51 | fix: resolve 28 TypeScript errors in ModuleLessonViewer and ScenarioSorter | 1 | 77 | 9
42 | 2026-03-22 22:32:25 | feat: add 250 anchor questions, fix length bias, and surface foundational questions first | 3 | 19352 | 1573
43 | 2026-03-23 01:34:14 | feat: module feedback cards, hint system, and struggling-skill alerts | 4 | 21974 | 21
44 | 2026-03-23 03:31:31 | feat: learning path interactives, question bank expansion, and module tracking | 11 | 21417 | 1210
45 | 2026-03-23 03:33:01 | fix: migration 0005 — use gen_random_uuid() and create learning_path_progress | 1 | 37 | 9
46 | 2026-03-23 03:37:18 | docs: sync documentation with current codebase state | 2 | 49 | 11
47 | 2026-03-23 04:10:03 | fix: UNUSED answer choices, login page sidebar scroll, sign-in panel sticky, stale copy | 2 | 7 | 7
48 | 2026-03-23 06:04:41 | feat: wire 27 interactive exercises into learning modules (D1–D4) | 2 | 424 | 20
49 | 2026-03-23 14:43:10 | Add vocabulary glossary with dynamic module tooltips | 10 | 5478 | 1016
50 | 2026-03-23 18:40:44 | feat: Redemption Rounds, Study Notebook, module interactives polish | 38 | 20436 | 1943
51 | 2026-03-24 08:26:47 | fix: consolidate assessment terminology to "adaptive diagnostic" throughout | 12 | 353 | 14506
52 | 2026-03-24 10:59:04 | fix: hide "Start diagnostic" card when a diagnostic is already in progress | 1 | 11 | 9
53 | 2026-03-24 11:24:11 | fix: restore clean repo state and track help faq | 6 | 101 | 1
54 | 2026-03-24 12:16:35 | fix: resolve CAT-4 type drift and CAT-3 label inconsistency | 5 | 33 | 6
55 | 2026-03-26 17:32:25 | refactor: replace hardcoded proficiency thresholds with canonical constants | 4 | 22 | 18
56 | 2026-03-26 18:51:54 | feat: add 3-layer admin analytics to dashboard | 7 | 1469 | 17
57 | 2026-03-26 18:54:14 | fix: tighten diagnostic assessment layout to reduce required scrolling | 2 | 10 | 10
58 | 2026-03-27 00:52:01 | feat: make users-online pill time-of-day aware | 1 | 100 | 10
59 | 2026-03-27 00:54:28 | fix: restore adaptive diagnostic resume across browser sessions | 10 | 303 | 23
60 | 2026-03-27 00:55:15 | feat: add Tutor Chat with skill-aware AI, quiz engine, and proactive insights | 16 | 2230 | 0
61 | 2026-03-27 07:52:40 | feat: improve AI Tutor — fix quiz routing, artifact generation, and chip UX | 8 | 814 | 80
62 | 2026-03-27 08:06:18 | chore: add exports/ to .gitignore and add audit-user-responses script | 2 | 208 | 0
63 | 2026-03-27 11:16:59 | fix: normalize artifact types from Claude + guard fill-in-blank download | 2 | 37 | 2
64 | 2026-03-27 11:27:45 | fix: harden tutor against null correct_answer, empty quiz pool, and missing chips | 1 | 15 | 2
65 | 2026-03-27 23:55:42 | feat: Redemption Rounds v2 — quarantine system with blacklist exclusion | 5 | 272 | 105
66 | 2026-03-27 23:56:42 | feat: leaderboard — replace fake seeded data with real API | 3 | 316 | 74
67 | 2026-03-27 23:56:55 | feat: Vocabulary Quiz Mode in Glossary | 3 | 850 | 100
68 | 2026-03-27 23:57:07 | feat: AI Tutor — smarter artifact skill targeting and artifact fixes | 7 | 433 | 52
69 | 2026-03-27 23:57:17 | feat: Admin — AI Tutor Chat Activity tab | 3 | 547 | 2
70 | 2026-03-27 23:57:37 | feat: Concept Analytics panel in Results Dashboard | 3 | 422 | 1
71 | 2026-03-27 23:58:09 | feat: remove Spicy Mode, refresh home dashboard, misc UX fixes | 17 | 9328 | 332
72 | 2026-03-29 10:42:35 | refactor: learning science alignment — P1–P6 | 34 | 744 | 257
73 | 2026-03-29 10:44:34 | docs: update CLAUDE.md hook name reference after P5 rename | 1 | 1 | 1